Cherry — DealFlow
Jira Master Backlog & Sprint Addition Plan

Version 1.0 | 27 September 2026 | Team-managed Scrum space DF

# Purpose

Use this document as the authoritative checklist for populating the existing DealFlow Jira software space. The current team-managed space does not expose Releases/Versions, so release milestones are represented by epics and sprints. Do not create fake versions.

# Jira standards

| Area | Standard |
| --- | --- |
| Method | Scrum |
| Hierarchy | Epic → Story/Task → Subtask; Bug/Spike when needed |
| Estimation | Story points: 1, 2, 3, 5, 8, 13 |
| Priority | P0 Critical / P1 High / P2 Medium / P3 Later |
| Workflow | BACKLOG → READY → IN PROGRESS → CODE COMPLETE → TESTING → REVIEW → DONE |
| Branch | feature/DF-<id>-<short-name>; fix/DF-<id>-<short-name> |
| Commit | type(scope): description |
| Release tracking | Sprint + Epic structure |

# Sprint master list

| ID | Sprint | Dates | Milestone |
| --- | --- | --- | --- |
| S00 | DF-S00 — Jira & Engineering Setup | 27 Sep 2026 | R0 |
| S01 | DF-S01 — Platform Foundation | 28 Sep–04 Oct | R1 |
| S02 | DF-S02 — Identity & Tenancy | 05–11 Oct | R1 |
| S03 | DF-S03 — Contacts & Customers | 12–18 Oct | R1.1 |
| S04 | DF-S04 — Lead Management | 19–25 Oct | R1.1 |
| S05 | DF-S05 — Requirements & Properties | 26 Oct–01 Nov | R1.2 |
| S06 | DF-S06 — Data Import | 02–08 Nov | R1.2 |
| S07 | DF-S07 — Lead Operations & Timeline | 09–15 Nov | R1.2 |
| S08 | DF-S08 — Follow-ups & Today’s Attention | 16–22 Nov | R1.2 |
| S09 | DF-S09 — Matching | 23–29 Nov | R1.3 |
| S10 | DF-S10 — Site Visits | 30 Nov–06 Dec | R1.3 |
| S11 | DF-S11 — Deal Workspace | 07–13 Dec | R2 |
| S12 | DF-S12 — Documents | 14–20 Dec | R2 |
| S13 | DF-S13 — Automation | 21–27 Dec | R2 |
| S14 | DF-S14 — Billing & Entitlements | 28 Dec–03 Jan | R2 |
| S15 | DF-S15 — Cherry Control Plane | 04–10 Jan | R2 |
| S16 | DF-S16 — Security & Production Readiness | 11–17 Jan | R2+ |
| S17 | DF-S17 — AI Assistance Foundation | 18–24 Jan | R1.3 |
| S18 | DF-S18 — AI Workflow Assistance | 25–31 Jan | R1.3 |
| S19 | DF-S19 — Integrations | 01–07 Feb | R2+ |
| S20 | DF-S20 — Scale & Reliability | 08–14 Feb | R2+ |

# Epic master list

| Epic key | Epic name | Priority |
| --- | --- | --- |
| DF-E01 | Platform Foundation | P0 |
| DF-E02 | Identity & Tenancy | P0 |
| DF-E03 | Contacts & Customers | P0 |
| DF-E04 | Lead Management | P0 |
| DF-E05 | Customer Requirements | P0 |
| DF-E06 | Property Management | P0 |
| DF-E07 | Data Import | P0 |
| DF-E08 | Property Matching | P1 |
| DF-E09 | Follow-Up Intelligence | P0 |
| DF-E10 | Timeline & Activity | P1 |
| DF-E11 | Pipeline & Today’s Attention | P0 |
| DF-E12 | Documents | P1 |
| DF-E13 | Dashboard & Analytics | P1 |
| DF-E14 | End-to-End QA | P0 |
| DF-E15 | Security & Production Hardening | P0 |
| DF-E16 | Deployment & Launch | P0 |
| DF-E17 | Site Visits | P1 |
| DF-E18 | Deal Workspace | P0 |
| DF-E19 | Notifications & Bulk Operations | P1 |
| DF-E20 | Automation | P1 |
| DF-E21 | Roles, Permissions & Approvals | P1 |
| DF-E22 | Advanced Import | P2 |
| DF-E23 | Integrations | P2 |
| DF-E24 | AI Assistance | P1 |
| DF-E25 | Billing & Entitlements | P1 |
| DF-E26 | Cherry Control Plane | P1 |
| DF-E27 | Scale & Reliability | P1 |

# Master story backlog

| Sprint | Epic | Story | SP | Priority |
| --- | --- | --- | --- | --- |
| S00 | SETUP | Create/verify DealFlow Scrum configuration | 1 | P0 |
| S00 | SETUP | Create engineering repository structure | 2 | P0 |
| S00 | SETUP | Define Git branching and commit standards | 1 | P0 |
| S00 | SETUP | Create ADR structure | 1 | P1 |
| S00 | SETUP | Create Definition of Ready and Done | 1 | P0 |
| S00 | SETUP | Create CI baseline | 2 | P0 |
| S00 | SETUP | Create local development environment | 2 | P0 |
| S01 | DF-E01 | Bootstrap FastAPI backend | 3 | P0 |
| S01 | DF-E01 | Bootstrap React TypeScript frontend | 3 | P0 |
| S01 | DF-E01 | Configure PostgreSQL integration | 3 | P0 |
| S01 | DF-E01 | Configure SQLAlchemy and Alembic | 3 | P0 |
| S01 | DF-E01 | Create shared configuration and environment handling | 2 | P0 |
| S01 | DF-E01 | Create API error handling baseline | 2 | P1 |
| S01 | DF-E01 | Create structured logging baseline | 2 | P1 |
| S01 | DF-E01 | Create frontend routing/layout baseline | 2 | P1 |
| S02 | DF-E02 | Implement user registration/invitation model | 3 | P0 |
| S02 | DF-E02 | Implement login/session flow | 5 | P0 |
| S02 | DF-E02 | Implement tenant model | 3 | P0 |
| S02 | DF-E02 | Implement tenant-scoped data access | 5 | P0 |
| S02 | DF-E02 | Implement membership model | 3 | P0 |
| S02 | DF-E02 | Implement baseline roles | 3 | P0 |
| S02 | DF-E02 | Add authentication security controls | 3 | P0 |
| S02 | DF-E02 | Add authorization tests | 3 | P0 |
| S03 | DF-E03 | Create contact model | 3 | P0 |
| S03 | DF-E03 | Create customer profile model | 3 | P0 |
| S03 | DF-E03 | Create contact list/search | 3 | P0 |
| S03 | DF-E03 | Create contact detail view | 3 | P0 |
| S03 | DF-E03 | Create duplicate detection baseline | 3 | P1 |
| S03 | DF-E03 | Create contact activity history | 2 | P1 |
| S04 | DF-E04 | Create lead model | 3 | P0 |
| S04 | DF-E04 | Create lead lifecycle states | 3 | P0 |
| S04 | DF-E04 | Link lead to contact/customer | 2 | P0 |
| S04 | DF-E04 | Create lead list and filters | 3 | P0 |
| S04 | DF-E04 | Create lead detail workspace | 5 | P0 |
| S04 | DF-E04 | Separate interest from lead status | 2 | P0 |
| S04 | DF-E04 | Add lead ownership controls | 2 | P1 |
| S05 | DF-E05 | Create customer requirement model | 3 | P0 |
| S05 | DF-E05 | Support budget/location/size criteria | 3 | P0 |
| S05 | DF-E05 | Link requirement to lead/customer | 2 | P0 |
| S05 | DF-E06 | Create property model | 5 | P0 |
| S05 | DF-E06 | Create property status/availability model | 3 | P0 |
| S05 | DF-E06 | Create property list/search | 3 | P0 |
| S05 | DF-E06 | Create property detail view | 3 | P0 |
| S05 | DF-E05 | Create requirement history | 2 | P1 |
| S06 | DF-E07 | Create import batch model | 3 | P0 |
| S06 | DF-E07 | Upload CSV/XLSX source | 3 | P0 |
| S06 | DF-E07 | Detect columns and preview mapping | 5 | P0 |
| S06 | DF-E07 | Validate imported rows | 5 | P0 |
| S06 | DF-E07 | Import contacts without activating leads | 5 | P0 |
| S06 | DF-E07 | Preserve source/provenance metadata | 3 | P0 |
| S06 | DF-E07 | Provide import result summary | 2 | P1 |
| S06 | DF-E07 | Support safe re-run/idempotency baseline | 3 | P1 |
| S07 | DF-E10 | Create activity/timeline model | 3 | P0 |
| S07 | DF-E10 | Show lead timeline | 3 | P0 |
| S07 | DF-E10 | Record status/owner changes | 2 | P0 |
| S07 | DF-E11 | Create operational pipeline view | 5 | P0 |
| S07 | DF-E11 | Create next-action model | 3 | P0 |
| S07 | DF-E11 | Create Today’s Attention view | 5 | P0 |
| S08 | DF-E09 | Create follow-up model | 3 | P0 |
| S08 | DF-E09 | Create follow-up creation flow | 3 | P0 |
| S08 | DF-E09 | Complete/reschedule follow-up | 3 | P0 |
| S08 | DF-E09 | Track overdue follow-ups | 2 | P0 |
| S08 | DF-E09 | Require next action after key outcomes | 3 | P1 |
| S08 | DF-E11 | Improve Today’s Attention prioritization | 3 | P1 |
| S08 | DF-E19 | Add bulk follow-up operations | 3 | P1 |
| S09 | DF-E08 | Create matching criteria engine | 5 | P0 |
| S09 | DF-E08 | Generate property match results | 5 | P0 |
| S09 | DF-E08 | Allow manual shortlist | 3 | P0 |
| S09 | DF-E08 | Record match history | 2 | P1 |
| S09 | DF-E08 | Prevent unauthorized cross-tenant matching | 2 | P0 |
| S10 | DF-E17 | Create site visit model | 3 | P0 |
| S10 | DF-E17 | Schedule site visit | 3 | P0 |
| S10 | DF-E17 | Record attendance/outcome | 3 | P0 |
| S10 | DF-E17 | Create post-visit follow-up | 3 | P0 |
| S10 | DF-E17 | Show visit history | 2 | P1 |
| S11 | DF-E18 | Create deal model | 5 | P0 |
| S11 | DF-E18 | Create negotiation state | 3 | P0 |
| S11 | DF-E18 | Create booking/deal workflow | 5 | P0 |
| S11 | DF-E18 | Track payment milestones | 3 | P1 |
| S11 | DF-E18 | Track commission | 3 | P1 |
| S11 | DF-E18 | Close deal | 3 | P0 |
| S11 | DF-E18 | Create referral record | 2 | P2 |
| S12 | DF-E12 | Create document metadata model | 3 | P1 |
| S12 | DF-E12 | Implement secure object storage abstraction | 5 | P1 |
| S12 | DF-E12 | Upload document | 3 | P1 |
| S12 | DF-E12 | Download document with authorization | 3 | P0 |
| S12 | DF-E12 | Audit document access | 2 | P0 |
| S12 | DF-E12 | Link documents to lead/property/deal | 3 | P1 |
| S13 | DF-E20 | Create automation rule model | 3 | P1 |
| S13 | DF-E20 | Implement event-driven trigger baseline | 5 | P1 |
| S13 | DF-E20 | Create follow-up automation | 3 | P1 |
| S13 | DF-E19 | Create in-app notifications | 3 | P1 |
| S13 | DF-E19 | Add notification preferences | 2 | P2 |
| S13 | DF-E20 | Add automation audit trail | 2 | P0 |
| S14 | DF-E25 | Create subscription model | 3 | P1 |
| S14 | DF-E25 | Create plan/entitlement model | 3 | P1 |
| S14 | DF-E25 | Implement provider adapter boundary | 3 | P1 |
| S14 | DF-E25 | Implement webhook verification/idempotency | 5 | P0 |
| S14 | DF-E25 | Enforce tenant entitlements | 5 | P1 |
| S14 | DF-E25 | Create billing audit/reconciliation records | 3 | P1 |
| S15 | DF-E26 | Create Cherry internal admin model | 3 | P1 |
| S15 | DF-E26 | Create tenant administration view | 5 | P1 |
| S15 | DF-E26 | Create support/audit access boundary | 5 | P0 |
| S15 | DF-E26 | Create tenant lifecycle controls | 3 | P1 |
| S15 | DF-E26 | Create internal audit view | 3 | P1 |
| S16 | DF-E15 | Run dependency/security scanning | 3 | P0 |
| S16 | DF-E15 | Harden authentication/session controls | 3 | P0 |
| S16 | DF-E15 | Verify tenant isolation with negative tests | 5 | P0 |
| S16 | DF-E15 | Add rate limiting baseline | 3 | P1 |
| S16 | DF-E15 | Add secret/configuration audit | 2 | P0 |
| S16 | DF-E14 | Create end-to-end critical journey tests | 5 | P0 |
| S16 | DF-E16 | Create production deployment checklist | 3 | P0 |
| S17 | DF-E24 | Define AI identity/permission boundary | 3 | P0 |
| S17 | DF-E24 | Create AI request/audit model | 3 | P0 |
| S17 | DF-E24 | Create AI provider abstraction | 3 | P1 |
| S17 | DF-E24 | Add AI safety/policy gate | 5 | P0 |
| S17 | DF-E24 | Create AI evaluation dataset structure | 3 | P1 |
| S18 | DF-E24 | Generate lead summary | 3 | P1 |
| S18 | DF-E24 | Suggest next action | 5 | P1 |
| S18 | DF-E24 | Draft follow-up message | 3 | P1 |
| S18 | DF-E24 | Summarize property/requirement match | 3 | P1 |
| S18 | DF-E24 | Add human approval for consequential AI actions | 5 | P0 |
| S19 | DF-E23 | Define integration adapter contract | 3 | P1 |
| S19 | DF-E23 | Create webhook ingestion boundary | 3 | P1 |
| S19 | DF-E23 | Create outbound event model | 3 | P1 |
| S19 | DF-E23 | Add integration audit trail | 2 | P1 |
| S20 | DF-E27 | Define performance budgets | 2 | P1 |
| S20 | DF-E27 | Add database query/index review | 3 | P1 |
| S20 | DF-E27 | Add background job execution baseline | 5 | P1 |
| S20 | DF-E27 | Add observability metrics | 3 | P0 |
| S20 | DF-E27 | Add resilience/retry strategy | 3 | P1 |
| S20 | DF-E27 | Create backup/restore verification | 3 | P0 |

# Backlog to add later

| Epic | Item | Priority |
| --- | --- | --- |
| DF-E19 | Advanced email/SMS/WhatsApp notification adapters | P2 |
| DF-E22 | Recurring/scheduled imports | P2 |
| DF-E22 | Advanced field transformation rules | P2 |
| DF-E22 | Import review/approval queue | P2 |
| DF-E21 | Fine-grained permission matrix | P2 |
| DF-E21 | Approval workflows for sensitive operations | P2 |
| DF-E23 | CRM/accounting/communication integrations | P2 |
| DF-E24 | AI-assisted duplicate resolution | P2 |
| DF-E24 | AI-assisted data quality suggestions | P2 |
| DF-E24 | AI workflow copilot | P2 |
| DF-E27 | Horizontal scaling strategy | P2 |
| DF-E27 | Disaster recovery exercise | P1 |
| DF-E13 | Advanced analytics/reporting | P2 |

# Definition of Ready

Clear business/user outcome.

Testable acceptance criteria.

Dependencies identified.

Small enough for one sprint.

Story points and priority assigned.

Security/data/API/UX considerations identified.

No unresolved blocker prevents implementation.

# Definition of Done

Implementation complete and follows architecture standards.

Relevant unit/integration/frontend/E2E tests added or updated.

Authorization and tenant-isolation behavior tested where applicable.

Validation and error handling implemented.

Logging/audit behavior implemented where required.

Database migration included for schema changes.

Code reviewed and CI checks pass.

Documentation/ADR updated when required.

No known P0/P1 defect remains open against the story.

Acceptance criteria verified and Jira issue moved to DONE.

# V1 release gate

Authentication and exactly-scoped tenant access work.

Contacts, leads, requirements and properties work.

Historical imports preserve provenance and do not automatically activate leads.

Matching produces explainable results.

Follow-ups and next actions work and appear in Today’s Attention.

Timeline/history is trustworthy.

Site visit → negotiation → deal/closure journey works.

Documents are access-controlled and audited.

Critical end-to-end tests pass.

Security and tenant-isolation tests pass.

Deployment and rollback procedures are documented and tested.

# Product constraints — always active

No silent destructive migrations.

Backward compatibility for existing tenant data/workflows.

Future data must coexist with earlier models where required.

No uncontrolled cross-tenant access.

No ambiguous ownership of active opportunities.

Active opportunities should have a clear next action where the workflow requires one.

Imported/historical data retains provenance.

AI inherits identity, permissions, policy, context and audit boundaries.

Customer experience stays simple even when internal architecture is complex.

Security, observability, testing and reliability are continuous.

# Exact population order

1. Keep the current DealFlow Scrum settings unchanged.

2. Create/rename the empty setup sprint as DF-S00 — Jira & Engineering Setup.

3. Create DF-E01 through DF-E27.

4. Create DF-S01 through DF-S20.

5. Add the S00 setup tasks.

6. Add S01–S20 stories from the Master Story Backlog.

7. Link every story to its Epic and Sprint.

8. Set priority and story points.

9. Write a sprint goal before starting each sprint.

10. Do not start a sprint until its backlog is refined and ready.

# Important

Do not configure custom Jira fields, custom filters, Jira automation, or external toolchain integrations yet unless a concrete need appears. Do not create fake Releases/Versions. We will keep the current space simple and execute through disciplined Scrum.