CHERRY

DealFlow — Master Jira Planning & Execution Plan

Releases • Sprints • Epics • Features • User Stories • Tasks • Dependencies • Estimates • Acceptance Criteria

Version 1.0 | Planning baseline | Accelerated product execution

# 1. Purpose

This document is the complete planning source for setting up the DealFlow Jira project. It intentionally contains planning structure rather than Jira configuration instructions. Jira should be configured from this document first; implementation begins only after the initial planning structure is loaded.

Primary objective: move from a blank Jira project to a controlled, traceable product-delivery system, then execute DealFlow V1 as quickly as practical.

# 2. Product Definition

DealFlow is a configurable real-estate business operating platform that organizes existing and new business data, manages the lead-to-deal lifecycle, ensures every opportunity has a clear next action, and brings contacts, leads, requirements, properties, follow-ups, visits, documents and deals into one simple workspace.

Core V1 promise: Manage every real-estate opportunity from first contact to closure without losing history, follow-ups, documents, ownership or next action.

# 3. Planning Principles

Build small, release early, measure real usage, improve continuously.

V1 is a usable release milestone, not the end of the product.

Keep the customer experience simple; complexity belongs inside the system.

Historical/imported data and actively managed data must remain distinguishable.

Every important active record should have status, owner, next action, timing and history.

Use a modular monolith initially; extract services only when evidence justifies it.

Security, tenant isolation, testing, observability and auditability are part of delivery, not post-release work.

One story at a time: implement, test, validate, commit, close.

Do not allow low-priority features to interrupt the V1 critical path.

Avoid premature microservices, advanced AI and complex infrastructure during the accelerated V1 build.

# 4. Jira Hierarchy

| Level | Purpose | Example |
| --- | --- | --- |
| Release | Commercial/product milestone | R1 — DealFlow V1 |
| Sprint | Time-boxed delivery increment | DF-S01 — V1 Core Product |
| Epic | Major capability | DF-E04 — Lead Management |
| Feature | Capability within an epic | Lead lifecycle |
| Story | User-visible requirement | As an agent, I can create a lead |
| Task | Engineering implementation | Create lead service |
| Sub-task | Small implementation step | Add validation tests |
| Bug | Defect | Prevent duplicate lead creation |
| Spike | Time-boxed investigation | Evaluate import parsing approach |

# 5. Releases

| Release | Name | Target | Exit Objective |
| --- | --- | --- | --- |
| R0 | Planning & Engineering Setup | 27 Sep 2026 | Jira, repository, environments, CI, development standards and test foundation ready. |
| R1 | DealFlow V1 | 28 Sep–11 Oct 2026 | Complete core real-estate opportunity workflow and deployable V1. |
| R1.1 | Operational Expansion | 12–25 Oct 2026 | Site visits, feedback, deal workspace, notifications and bulk operations. |
| R1.2 | Automation & Integration | 26 Oct–22 Nov 2026 | Automation, roles, permissions, approvals, advanced import and integrations. |
| R1.3 | AI-Assisted DealFlow | 23 Nov–6 Dec 2026 | AI extraction, summaries, matching assistance, next actions and drafting. |
| R2 | Commercial Platform | After R1.3 | Billing, entitlements, Cherry Control Plane and deeper operational capabilities. |
| R2+ | Scale & Continuous Evolution | Ongoing | Reliability, performance, new industries, advanced workflows and evidence-driven product evolution. |

# 6. Sprint Calendar

| Sprint | Name | Dates | Goal | Release |
| --- | --- | --- | --- | --- |
| DF-S00 | Jira & Engineering Setup | 27 Sep | Planning baseline and development foundation complete | R0 |
| DF-S01 | DealFlow V1 — Core Build | 28 Sep–11 Oct | Complete end-to-end V1 workflow | R1 |
| DF-S02 | Operational Expansion | 12–25 Oct | Visits, feedback, deal workspace, notifications | R1.1 |
| DF-S03 | Automation & Access | 26 Oct–8 Nov | Automation, roles, permissions, approvals | R1.2 |
| DF-S04 | Data & Integrations | 9–22 Nov | Advanced import and high-value integrations | R1.2 |
| DF-S05 | AI Foundation | 23 Nov–6 Dec | AI-assisted workflows with permission boundaries | R1.3 |
| DF-S06 | Billing Foundation | Post-S05 | Plans, subscriptions, entitlements and payment lifecycle | R2 |
| DF-S07 | Cherry Control Plane | Post-S06 | Internal customer, tenant, billing and operational control plane | R2 |
| DF-S08+ | Scale & Continuous Improvement | Ongoing | Reliability, performance, analytics and product evolution | R2+ |

# 7. Estimation & Priority Rules

| Priority | Meaning | Use |
| --- | --- | --- |
| P0 | Critical | Required for V1 workflow, security, data integrity or production readiness. |
| P1 | High | Important for usable operations; may follow immediately after V1. |
| P2 | Medium | V1.2/V1.3 capability or validated customer demand. |
| P3 | Later | Future opportunity; do not interrupt committed work. |

Story points: 1, 2, 3, 5, 8, 13. Stories above 13 points must be decomposed. Estimates are planning aids, not delivery guarantees.

# 8. Complete Epic Catalog

| ID | Epic | Priority | Release | Description |
| --- | --- | --- | --- | --- |
| DF-E01 | Platform Foundation | P0 | R0/R1 | Technical foundation used by all product modules. |
| DF-E02 | Identity & Tenancy | P0 | R1 | Authentication, users, organizations, memberships and tenant isolation. |
| DF-E03 | Contacts & Customers | P0 | R1 | People and customer records, ownership, search and history. |
| DF-E04 | Lead Management | P0 | R1 | Lead lifecycle, ownership, qualification, interest and outcomes. |
| DF-E05 | Customer Requirements | P0 | R1 | Structured requirements that drive property matching. |
| DF-E06 | Property Management | P0 | R1 | Property inventory, availability, search and ownership/source. |
| DF-E07 | Data Import | P0 | R1 | Safe onboarding of existing CSV/XLSX data with provenance and review. |
| DF-E08 | Property Matching | P0 | R1 | Requirement-to-property matching with transparent reasons. |
| DF-E09 | Follow-Up Intelligence | P0 | R1 | Due, overdue, upcoming and recommended next actions. |
| DF-E10 | Timeline & Activity | P0 | R1 | Chronological business history and auditable activities. |
| DF-E11 | Pipeline & Today's Attention | P0 | R1 | Opportunity pipeline and daily operational focus. |
| DF-E12 | Documents | P1 | R1 | Basic document lifecycle and association with records. |
| DF-E13 | Dashboard & Analytics | P1 | R1 | Basic operational metrics and dashboard. |
| DF-E14 | End-to-End QA | P0 | R1 | Critical journeys, regression and release validation. |
| DF-E15 | Security & Production Hardening | P0 | R1 | Tenant isolation, security checks, secrets, logging and hardening. |
| DF-E16 | Deployment & Launch | P0 | R1 | Staging/production deployment, smoke tests, rollback and launch readiness. |
| DF-E17 | Site Visits | P1 | R1.1 | Visit scheduling, reminders, attendance, feedback and next action. |
| DF-E18 | Deal Workspace | P1 | R1.1 | Negotiation, documents, tasks, payments/commission placeholders and deal history. |
| DF-E19 | Notifications & Bulk Operations | P1 | R1.1 | Operational notifications and efficient bulk actions. |
| DF-E20 | Automation | P2 | R1.2 | Rule/trigger/action workflows without customer-specific code. |
| DF-E21 | Roles, Permissions & Approvals | P2 | R1.2 | Granular access and approval controls. |
| DF-E22 | Advanced Import | P2 | R1.2 | Merge, rollback, mapping templates, advanced validation. |
| DF-E23 | Integrations | P2 | R1.2 | Validated high-value external integrations. |
| DF-E24 | AI Assistance | P2 | R1.3 | AI extraction, summaries, recommendations and drafting. |
| DF-E25 | Billing & Entitlements | P2 | R2 | Plans, subscriptions, provider events, invoices, access and recovery. |
| DF-E26 | Cherry Control Plane | P2 | R2 | Internal tenant, customer, billing, support, audit and operational control. |
| DF-E27 | Scale & Reliability | P2 | R2+ | Performance, resilience, observability, backup/recovery and capacity. |

# 9. Release R0 — Planning & Engineering Setup

Goal: Jira and engineering can support controlled development without repeatedly stopping for setup.

| Story | Summary | Priority | Points | Acceptance |
| --- | --- | --- | --- | --- |
| DF-001 | Create DealFlow Jira project | P0 | 2 | Project exists with Scrum board and standard issue hierarchy. |
| DF-002 | Define Jira workflow | P0 | 2 | Backlog → Ready → In Progress → Code Complete → Testing → Review → Done. |
| DF-003 | Create releases/versions | P0 | 1 | R0, R1, R1.1, R1.2, R1.3 and R2 exist. |
| DF-004 | Create components and labels | P0 | 1 | Controlled component/label vocabulary exists. |
| DF-005 | Create DoR and DoD | P0 | 2 | Ready and Done criteria are documented. |
| DF-006 | Create repository | P0 | 2 | DealFlow GitHub repository exists with main/develop. |
| DF-007 | Define Git conventions | P0 | 1 | Branch, commit and PR conventions documented. |
| DF-008 | Bootstrap backend | P0 | 3 | FastAPI application runs locally. |
| DF-009 | Bootstrap frontend | P0 | 3 | React/TypeScript/Vite application runs locally. |
| DF-010 | Bootstrap PostgreSQL/Alembic | P0 | 3 | Database and migration workflow work locally. |
| DF-011 | Create Docker development environment | P0 | 3 | Required services start reproducibly. |
| DF-012 | Create CI foundation | P0 | 3 | Tests/lint/build execute on push/PR. |
| DF-013 | Create test foundation | P0 | 2 | Backend/frontend test frameworks run. |
| DF-014 | Create environment configuration | P0 | 2 | Local/staging configuration pattern exists. |
| DF-015 | Create development documentation | P1 | 2 | README and contribution workflow are usable. |

# 10. Release R1 — DealFlow V1 Complete Story Backlog

The following stories form the V1 implementation baseline. Technical tasks should be created beneath these stories during refinement; the story remains the customer-facing unit of completion.

## DF-E01 Platform Foundation

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-101 | Create application configuration system | P0 | 3 |
| DF-102 | Create database base model and UUID strategy | P0 | 3 |
| DF-103 | Create migration conventions | P0 | 2 |
| DF-104 | Create API error/validation conventions | P0 | 3 |
| DF-105 | Create health and readiness endpoints | P0 | 2 |
| DF-106 | Create structured application logging | P0 | 3 |
| DF-107 | Create API test harness | P0 | 3 |

## DF-E02 Identity & Tenancy

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-111 | Create organization/tenant model | P0 | 5 |
| DF-112 | Create user model | P0 | 3 |
| DF-113 | Create membership model | P0 | 3 |
| DF-114 | Implement authentication | P0 | 5 |
| DF-115 | Implement current-user context | P0 | 3 |
| DF-116 | Implement tenant context and isolation | P0 | 5 |
| DF-117 | Test unauthorized and cross-tenant access | P0 | 5 |

## DF-E03 Contacts & Customers

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-121 | Create contact record | P0 | 3 |
| DF-122 | Create customer profile | P0 | 3 |
| DF-123 | Assign owner to contact/customer | P0 | 2 |
| DF-124 | Search and filter contacts | P0 | 3 |
| DF-125 | Create contact history foundation | P0 | 3 |
| DF-126 | Detect likely duplicate contacts | P1 | 5 |

## DF-E04 Lead Management

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-131 | Create lead from contact | P0 | 3 |
| DF-132 | Implement lead lifecycle statuses | P0 | 3 |
| DF-133 | Store lead interest separately from status | P0 | 2 |
| DF-134 | Store lead outcome separately from status | P0 | 2 |
| DF-135 | Assign lead owner | P0 | 2 |
| DF-136 | Create lead notes and source | P0 | 2 |
| DF-137 | Search/filter leads | P0 | 3 |

## DF-E05 Customer Requirements

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-141 | Create customer requirement | P0 | 5 |
| DF-142 | Capture budget range | P0 | 2 |
| DF-143 | Capture location preferences | P0 | 2 |
| DF-144 | Capture property type/BHK/preferences | P0 | 3 |
| DF-145 | Capture possession/parking preferences | P0 | 2 |
| DF-146 | Associate requirement with lead/customer | P0 | 2 |
| DF-147 | Edit requirement while preserving history | P0 | 3 |

## DF-E06 Property Management

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-151 | Create property record | P0 | 5 |
| DF-152 | Capture property commercial fields | P0 | 3 |
| DF-153 | Capture property location and attributes | P0 | 3 |
| DF-154 | Track property availability/status | P0 | 3 |
| DF-155 | Search/filter properties | P0 | 5 |
| DF-156 | Associate property source/owner | P0 | 2 |

## DF-E07 Data Import

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-161 | Upload CSV/XLSX file | P0 | 5 |
| DF-162 | Analyze imported columns | P0 | 5 |
| DF-163 | Suggest and edit field mappings | P0 | 5 |
| DF-164 | Validate records before import | P0 | 5 |
| DF-165 | Preview import results | P0 | 3 |
| DF-166 | Create import batch/provenance record | P0 | 3 |
| DF-167 | Import records without silent overwrite | P0 | 5 |
| DF-168 | Mark imported records for review | P0 | 3 |
| DF-169 | Allow user to activate imported contact as lead | P0 | 3 |

## DF-E08 Property Matching

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-171 | Match requirement to properties | P0 | 5 |
| DF-172 | Rank matching properties | P0 | 5 |
| DF-173 | Show match reasons | P0 | 3 |
| DF-174 | Filter match results | P0 | 3 |

## DF-E09 Follow-Up Intelligence

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-181 | Create follow-up | P0 | 3 |
| DF-182 | Set follow-up due date/time | P0 | 2 |
| DF-183 | Track due/overdue/upcoming state | P0 | 3 |
| DF-184 | Complete follow-up with outcome | P0 | 3 |
| DF-185 | Set next action | P0 | 3 |
| DF-186 | Associate follow-up with lead/customer/property | P0 | 3 |

## DF-E10 Timeline & Activity

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-191 | Create activity event model | P0 | 3 |
| DF-192 | Record key lifecycle events | P0 | 5 |
| DF-193 | Display chronological timeline | P0 | 3 |
| DF-194 | Preserve historical changes | P0 | 5 |

## DF-E11 Pipeline & Today's Attention

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-201 | Create pipeline stages | P0 | 3 |
| DF-202 | Move lead through pipeline | P0 | 3 |
| DF-203 | Build Today's Attention view | P0 | 5 |
| DF-204 | Show overdue actions | P0 | 3 |
| DF-205 | Show due-today actions | P0 | 3 |
| DF-206 | Show high-priority opportunities | P0 | 3 |
| DF-207 | Show pending operational work | P1 | 3 |

## DF-E12 Documents

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-211 | Upload document | P1 | 5 |
| DF-212 | Associate document with business record | P1 | 3 |
| DF-213 | Track document status | P1 | 3 |
| DF-214 | Preserve document metadata/history | P1 | 3 |

## DF-E13 Dashboard & Analytics

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-221 | Create operational dashboard | P1 | 5 |
| DF-222 | Show lead metrics | P1 | 2 |
| DF-223 | Show follow-up metrics | P1 | 2 |
| DF-224 | Show property/opportunity metrics | P1 | 2 |

## DF-E14 End-to-End QA

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-231 | Test import-to-lead journey | P0 | 5 |
| DF-232 | Test lead-to-requirement-to-match journey | P0 | 5 |
| DF-233 | Test follow-up completion journey | P0 | 3 |
| DF-234 | Test pipeline journey | P0 | 3 |
| DF-235 | Run regression suite | P0 | 5 |

## DF-E15 Security & Production Hardening

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-241 | Validate tenant isolation | P0 | 5 |
| DF-242 | Validate authentication/authorization failures | P0 | 5 |
| DF-243 | Harden secrets/configuration | P0 | 3 |
| DF-244 | Validate input handling and error exposure | P0 | 3 |
| DF-245 | Create security/audit logging baseline | P0 | 3 |
| DF-246 | Review dependencies and known vulnerabilities | P0 | 3 |

## DF-E16 Deployment & Launch

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-251 | Create staging deployment | P0 | 5 |
| DF-252 | Create production deployment | P0 | 5 |
| DF-253 | Run production migration safely | P0 | 3 |
| DF-254 | Run production smoke tests | P0 | 3 |
| DF-255 | Create rollback/recovery checklist | P0 | 3 |
| DF-256 | Create V1 release notes and known limitations | P0 | 2 |

# 11. Story Acceptance Criteria Template

Use this pattern when converting each story into Jira:

Given the required context, the user can perform the intended action.

Valid input is accepted and persisted correctly.

Invalid input returns a clear, safe error.

Authorization and tenant boundaries are enforced where applicable.

The resulting state is visible through the relevant UI/API.

Relevant history/audit information is retained.

Automated tests cover the main success and failure paths.

No critical regression is introduced.

# 12. R1.1 — Operational Expansion Stories

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-301 | Schedule a site visit | P1 | 5 |
| DF-302 | Confirm/cancel/reschedule a site visit | P1 | 3 |
| DF-303 | Record site visit feedback | P1 | 5 |
| DF-304 | Convert visit outcome into next action | P1 | 3 |
| DF-305 | Create deal workspace | P1 | 8 |
| DF-306 | Manage negotiation activities | P1 | 5 |
| DF-307 | Track deal documents | P1 | 3 |
| DF-308 | Create in-app notifications | P1 | 5 |
| DF-309 | Create bulk assignment operations | P1 | 3 |
| DF-310 | Create bulk status/update operations | P1 | 3 |

# 13. R1.2 — Automation, Access, Data & Integrations

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-401 | Create automation trigger model | P2 | 5 |
| DF-402 | Create automation action model | P2 | 5 |
| DF-403 | Create basic workflow rules | P2 | 8 |
| DF-404 | Create role model | P2 | 3 |
| DF-405 | Create permission model | P2 | 5 |
| DF-406 | Create approval rules | P2 | 5 |
| DF-407 | Create import merge workflow | P2 | 5 |
| DF-408 | Create import rollback capability | P2 | 5 |
| DF-409 | Create reusable import mappings | P2 | 3 |
| DF-410 | Create integration adapter foundation | P2 | 5 |
| DF-411 | Implement first validated customer-demand integration | P2 | 8 |

# 14. R1.3 — AI-Assisted DealFlow

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-501 | Define AI context boundary | P2 | 5 |
| DF-502 | Enforce AI identity and permissions | P2 | 5 |
| DF-503 | Extract lead information from unstructured input | P2 | 8 |
| DF-504 | Extract customer requirement | P2 | 8 |
| DF-505 | Summarize lead/customer history | P2 | 5 |
| DF-506 | Assist property matching explanation | P2 | 8 |
| DF-507 | Recommend next action | P2 | 8 |
| DF-508 | Draft customer communication | P2 | 5 |
| DF-509 | Audit AI-assisted actions | P2 | 5 |
| DF-510 | Add AI failure/uncertainty handling | P2 | 5 |

# 15. R2 — Billing & Cherry Control Plane

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-601 | Create plan model | P2 | 3 |
| DF-602 | Create subscription model | P2 | 5 |
| DF-603 | Create entitlement model | P2 | 5 |
| DF-604 | Integrate payment provider adapter | P2 | 8 |
| DF-605 | Verify payment webhooks and idempotency | P2 | 5 |
| DF-606 | Create invoice/payment records | P2 | 5 |
| DF-607 | Implement renewal/recovery lifecycle | P2 | 8 |
| DF-608 | Implement cancellation/end-of-period behavior | P2 | 5 |
| DF-609 | Create Cherry customer/tenant control plane | P2 | 8 |
| DF-610 | Create support/security/audit views | P2 | 8 |
| DF-611 | Create internal usage/revenue metrics | P2 | 5 |

# 16. R2+ — Scale & Continuous Evolution

| Story | Summary | Priority | Points |
| --- | --- | --- | --- |
| DF-701 | Performance baseline and profiling | P2 | 5 |
| DF-702 | Database performance optimization | P2 | 5 |
| DF-703 | Caching where evidence supports it | P2 | 5 |
| DF-704 | Background job infrastructure where justified | P2 | 5 |
| DF-705 | Backup and restore validation | P0 | 5 |
| DF-706 | Disaster recovery exercise | P2 | 5 |
| DF-707 | Observability dashboards and alerting | P2 | 8 |
| DF-708 | Capacity and load testing | P2 | 8 |
| DF-709 | Reliability improvement backlog | P2 | 5 |
| DF-710 | Customer feedback/product analytics loop | P1 | 5 |

# 17. Sprint Goals & Exit Criteria

| Sprint | Goal | Exit |
| --- | --- | --- |
| S00 | All tooling and governance needed to start development is operational. | Jira, repo, CI, local stack, tests and conventions work. |
| S01 | A real-estate opportunity can be managed through the core V1 workflow. | Core entities, import, matching, follow-up, pipeline, attention, documents, QA and deployment complete. |
| S02 | Agents can execute visits and manage a deal workspace operationally. | Visit and deal journeys work end-to-end. |
| S03 | Customers can configure basic automation and access controls safely. | Rules, permissions and approvals are tested. |
| S04 | DealFlow can ingest complex data and connect to validated external systems. | Advanced import and first demanded integrations work. |
| S05 | AI reduces manual work without bypassing security or human control. | AI workflows have permission, uncertainty and audit boundaries. |
| S06 | DealFlow has a commercial subscription foundation. | Billing and entitlement lifecycle works. |
| S07 | Cherry can operate DealFlow as a product company. | Internal control plane supports customer, tenant, billing, support and audit operations. |
| S08+ | The product continuously improves based on evidence. | Reliability, analytics, performance and customer-driven roadmap operate continuously. |

# 18. Dependencies & Critical Path

The V1 critical path should be treated as the primary execution chain:

Platform Foundation → Identity/Tenancy → Contacts → Leads → Requirements → Properties → Import → Matching → Follow-ups → Timeline → Pipeline/Today's Attention → Documents/Dashboard → QA → Security → Deployment → V1.

Parallelizable work may proceed where it does not create dependency risk. Examples: frontend shell work can progress while backend foundation is being implemented; test scaffolding can progress alongside feature development; documentation can be updated continuously.

# 19. Definition of Ready

Problem and user value are clear.

Acceptance criteria are explicit.

Dependencies are identified.

Data model/API/UI impact is understood sufficiently.

Security/tenant implications are identified.

Test expectations are known.

Story is small enough to complete within the sprint.

# 20. Definition of Done

Implementation complete.

Automated tests complete at the appropriate level.

Validation and error handling complete.

Authorization and tenant isolation verified where relevant.

Audit/history/observability considered.

Migration and compatibility handled where relevant.

Documentation updated.

No known critical regression.

Git commit/PR complete.

Jira acceptance criteria verified and issue closed.

# 21. Branch & Commit Convention

| Work | Pattern | Example |
| --- | --- | --- |
| Feature | feature/DF-<id>-<short-name> | feature/DF-131-create-lead |
| Bug | fix/DF-<id>-<short-name> | fix/DF-205-overdue-filter |
| Documentation | docs/DF-<id>-<short-name> | docs/DF-005-definition-of-done |
| Chore | chore/DF-<id>-<short-name> | chore/DF-012-ci-foundation |

Commit convention: type(scope): description. Example: feat(leads): create lead lifecycle.

# 22. Daily Execution Cadence

| Time/Stage | Action |
| --- | --- |
| Start of day | Select the highest-priority unblocked story and confirm acceptance criteria. |
| Build | Implement the smallest complete slice. |
| Test | Run focused tests immediately; do not postpone testing until the end. |
| Integrate | Run relevant integration/regression checks. |
| Commit | Create a clear Git commit tied to the Jira issue. |
| End of day | Update Jira status, remaining work, blockers and next action. |
| Every 2 weeks | Review release outcome, customer evidence, metrics and backlog. |

# 23. V1 Release Gate

V1 is complete only when the following journey works in a deployed environment:

Sign in → create/import data → review imported records → activate lead → capture requirement → add/search property → match property → set interest → create follow-up → complete follow-up → view timeline → move pipeline stage → view Today's Attention → upload/manage basic document → view dashboard.

No critical tenant-isolation defect.

No critical data-loss defect.

Critical regression journeys pass.

Production migration is verified.

Rollback/recovery procedure exists.

Monitoring/logging baseline exists.

Known limitations are documented.

A real user can complete the core workflow without engineering intervention.

# 24. Backlog Governance

Do not pre-create hundreds of speculative tasks.

Create the master epics/releases now; refine stories immediately before their sprint.

Customer feedback, incidents, analytics and sales objections create new backlog input.

Every new item must receive priority and release assignment.

Scope changes during a sprint require an explicit tradeoff.

Technical debt is visible in Jira; it is not hidden.

Repeated service/manual work should be analyzed for productization rather than permanently absorbed into operations.

At each release review, decide what to keep, improve, remove or postpone.

# 25. Product Completion Roadmap

DealFlow is not considered permanently 'finished'. The completion model is staged:

| Stage | Meaning |
| --- | --- |
| V1 Complete | Core real-estate workflow is usable, tested and deployable. |
| V1.1 Complete | Operational workflows around visits and deals are substantially complete. |
| V1.2 Complete | Automation, access control and integrations provide scalable operations. |
| V1.3 Complete | AI assists high-value workflows within permission and audit boundaries. |
| R2 Complete | Commercial billing and Cherry internal operations are productized. |
| R2+ Continuous | Performance, reliability, customer feedback and new capabilities evolve continuously. |

# 26. Immediate Planning Sequence

2. Create the Jira project and Scrum board.

3. Create Releases R0, R1, R1.1, R1.2, R1.3, R2 and R2+.

4. Create the 27 master Epics.

5. Create Sprint S00 and its setup stories.

6. Create Sprint S01 and the V1 story backlog.

7. Load the acceptance-criteria template into the Jira story template.

8. Do not begin implementation until S00 is sufficiently configured.

9. Execute S00, then immediately begin S01.

10. Refine S02 only after the V1 path is underway; avoid speculative over-planning.

11. At V1 release, use real customer evidence to reprioritize R1.1 onward.

# 27. Final Operating Rule

The purpose of this Jira plan is not to create bureaucracy. It is to make rapid development controlled. Every piece of work should have a reason, owner, priority, release, acceptance criteria and completion state. The team can then move quickly without losing product direction, quality or traceability.

Build → Test → Release → Measure → Learn → Improve