## Read Me
DEALSFLO RELEASE 1 — JIRA BACKLOG v2.0
Planning baseline | 30 October 2026
Stretch target | 14 November 2026 (15 days)
Hard deadline | 29 November 2026 (30 days)
Contents | 15 proposed epics and 58 stories
Important | Planning keys only; map to Jira-generated keys on import.
Status truth | No story is marked Done by this workbook. Audit existing code and mark reused work Verified/Reused.
Scope rule | All optional AI and automation capabilities are disabled by default and require entitlement, organization enablement, configuration/publication, authorization, provider readiness, consent and budget gates.
Engineering rule | Inspect first; preserve dirty work; one vertical story at a time; tests, build, diff/status review; commit/push/merge only with explicit approval.

## Jira Backlog
Issue Key | Epic | Sprint | Summary | User Story / Scope | Acceptance Criteria | Priority | Story Points | Dependencies | Labels | Status
DFR1-001 | DFR1-E01 | S1 (Days 1-3) | Baseline both repositories and preserve current work | Inspect SIBVO and Dealsflo branches, worktrees, dirty files, migrations, tests, builds, running services and existing Jira work. No code changes during audit. | Evidence-backed Existing/Partial/Missing/Needs-validation matrix; exact commands/results; no destructive actions; all dirty work preserved. | P0 | 3 | None | audit,architecture,git | To Do
DFR1-002 | DFR1-E01 | S1 (Days 1-3) | Approve target architecture and ADR register | Document modular monolith boundaries, event/outbox pattern, AI execution, channel gateway, SIBVO contracts and disabled-by-default feature policy. | Architecture diagram, context/container/component views, data ownership map, API conventions and ADRs approved; no speculative microservices. | P0 | 3 | DFR1-001 | architecture,adr | To Do
DFR1-003 | DFR1-E01 | S1 (Days 1-3) | Define Release 1 environment and provider dependency matrix | Identify staging/prod, database, Redis/worker, object storage, LLM, Meta, email and telephony credentials/account prerequisites. | Each external dependency has owner, sandbox/prod status, required approval, fallback/test strategy and blocker date; secrets not committed. | P0 | 2 | DFR1-001 | devops,integration | To Do
DFR1-004 | DFR1-E12 | S1 (Days 1-3) | Verify SIBVO identity and organization contract | Verify stable SIBVO subject, organization, membership, product membership, token issuer/audience, callback, PKCE/state/nonce and explicit local mapping. | No email-only account linking; active membership and product access resolved server-side; contract and negative tests documented. | P0 | 3 | DFR1-001 | sibvo,auth,security | To Do
DFR1-005 | DFR1-E12 | S1 (Days 1-3) | Verify subscription, entitlement and seat enforcement contract | Inspect plan/version, trial, subscription, entitlement, seat assignment, revocation and usage event contracts. | SIBVO is authoritative; Dealsflo does not duplicate billing/subscription truth; fail-closed behavior and reconciliation documented. | P0 | 3 | DFR1-004 | sibvo,billing,entitlements | To Do
DFR1-006 | DFR1-E13 | S1 (Days 1-3) | Define disabled-by-default capability policy | Specify platform entitlement, org enablement, provider connection, resource configuration/publish, actor permission, consent and budget gates. | No optional AI/automation executes unless all applicable gates pass; manual CRM operations continue when AI is disabled; in-flight disable policy documented. | P0 | 3 | DFR1-002,DFR1-005 | governance,security | To Do
DFR1-007 | DFR1-E04 | S1 (Days 1-3) | Confirm communication providers and channel capability matrix | Choose official WhatsApp Business, Meta Messenger/Instagram, email and one telephony provider; validate supported webhook/send/call features. | Provider choices and API capabilities verified from official docs/accounts; approval, template, messaging-window, rate, region and cost constraints captured. | P0 | 2 | DFR1-003 | integration,provider | To Do
DFR1-008 | DFR1-E02 | S2 (Days 4-6) | Audit and close critical CRM vertical-slice gaps | Map contacts, leads, requirements, properties, pipeline, follow-ups, site visits, deals and commissions to actual code; fix only release-blocking gaps. | Existing functions reused; one testable real DB/API/UI journey works; no duplicate CRM model/service introduced. | P0 | 5 | DFR1-001 | crm,backend,frontend | To Do
DFR1-009 | DFR1-E03 | S2 (Days 4-6) | Implement channel identity and contact resolution | Represent verified phone/email/channel identifiers and link them to contacts with confidence and manual review for ambiguous matches. | Unique constraints scoped correctly; no weak auto-merge; audit provenance; one contact can have multiple leads/opportunities. | P0 | 5 | DFR1-008 | crm,identity | To Do
DFR1-010 | DFR1-E03 | S2 (Days 4-6) | Implement conversation, participant and message timeline | Create normalized conversations, participants, inbound/outbound messages, provider IDs, timestamps, attachments and delivery states. | Customer timeline unifies channel threads without losing channel/thread IDs; tenant isolation and pagination tested. | P0 | 5 | DFR1-009 | inbox,backend | To Do
DFR1-011 | DFR1-E04 | S2 (Days 4-6) | Build integration connection registry and secrets boundary | Store provider account metadata, scopes, connection status and secret references; implement connect/disconnect and health status. | Secrets never stored in plaintext DB/logs; org-scoped authorization; credential rotation/disconnect behavior; no fake connected state. | P0 | 3 | DFR1-007 | integration,security | To Do
DFR1-012 | DFR1-E04 | S2 (Days 4-6) | Build verified webhook ingress and normalized event envelope | Implement signature verification, raw event capture with redaction, provider event normalization, deduplication and correlation IDs. | Invalid signatures rejected; idempotent event processing; provider payload versioning; replay-safe storage and observability. | P0 | 5 | DFR1-011 | webhooks,eventing | To Do
DFR1-013 | DFR1-E01 | S2 (Days 4-6) | Implement transactional outbox and background execution foundation | Publish domain events reliably and execute background jobs with retries, timeouts and dead-letter visibility using the existing stack where possible. | DB commit and event publication cannot silently diverge; idempotency keys; retry policy; failure inspection and tests. | P0 | 5 | DFR1-002 | backend,events,workers | To Do
DFR1-014 | DFR1-E04 | S2 (Days 4-6) | Implement outbound communication adapter contract | Create provider-neutral send interface for message/email/call requests, delivery callbacks, templates and normalized errors. | Provider adapters conform to typed contracts; policy checked before send; delivery state updates; retry does not duplicate messages. | P0 | 5 | DFR1-012,DFR1-013 | integration,backend | To Do
DFR1-015 | DFR1-E06 | S3 (Days 7-9) | Build provider-independent AI gateway | Route text, embedding, speech and multimodal tasks through provider adapters with timeout, retry, fallback and structured outputs. | Provider/model configurable by task; secrets protected; token/audio/image/page usage captured; provider failure is handled safely. | P0 | 5 | DFR1-003,DFR1-006 | ai,gateway | To Do
DFR1-016 | DFR1-E06 | S3 (Days 7-9) | Implement tenant-scoped knowledge ingestion and retrieval | Ingest approved organization documents and knowledge sources; chunk, embed, index and retrieve with access filtering. | Retrieval enforces org and document permissions; sources/citations returned; deletion/retention behavior defined; prompt injection treated as untrusted. | P1 | 5 | DFR1-015 | rag,knowledge | To Do
DFR1-017 | DFR1-E13 | S3 (Days 7-9) | Implement AI usage ledger and organization budgets | Meter provider, model, task, tokens/audio/images/pages, org, user, agent and workflow; support quotas and threshold alerts. | Provider cost separated from customer credits; budgets enforced server-side; idempotent usage records; configurable 70/85/100 alerts. | P0 | 5 | DFR1-015,DFR1-005 | usage,billing | To Do
DFR1-018 | DFR1-E07 | S3 (Days 7-9) | Implement typed AI tool registry and authorization | Register approved CRM/search/matching/follow-up/message/call tools with schemas and permission policies. | No arbitrary SQL/code; tool args validated; tenant context trusted server-side; every action attributed to initiating user/agent. | P0 | 5 | DFR1-008,DFR1-006,DFR1-015 | agents,security | To Do
DFR1-019 | DFR1-E07 | S3 (Days 7-9) | Implement agent definitions, versioning and execution runtime | Support agent identity, instructions, model, knowledge, tools, trigger, budgets, autonomy, version, execution and trace. | Draft/publish/pause; execution trace and step states; cancel/timeout/retry; disabled agents cannot execute; tests for cross-tenant denial. | P0 | 5 | DFR1-018,DFR1-017 | agents,runtime | To Do
DFR1-020 | DFR1-E09 | S3 (Days 7-9) | Implement explainable lead qualification and priority scoring | Extract requirements and calculate initial explainable priority using configured rules/baselines, with evidence and confidence. | Insufficient data is labelled rule-based/baseline; factors, timestamp and version visible; human corrections captured for evaluation. | P0 | 5 | DFR1-008,DFR1-015 | predictive,crm | To Do
DFR1-021 | DFR1-E07 | S3 (Days 7-9) | Deliver core lead intake and qualification agents | Build receptionist, identity resolution, qualification and lead scoring agent templates using authorized tools. | Agents create/update only through CRM services; review uncertain extraction; execution metrics and failure reasons visible. | P0 | 5 | DFR1-019,DFR1-020 | agents,sales | To Do
DFR1-022 | DFR1-E09 | S3 (Days 7-9) | Deliver property matching and next-best-action recommendations | Match customer requirements to available inventory using hard constraints then explainable ranking. | Only active/available properties; match explanation and mismatch reasons; recommendation feedback captured; no invented inventory. | P0 | 5 | DFR1-008,DFR1-020 | predictive,matching | To Do
DFR1-023 | DFR1-E08 | S4 (Days 10-12) | Implement workflow definition schema and version lifecycle | Define typed triggers, conditions, branches, actions, agent nodes, delays, approvals, retries and publish lifecycle. | Draft/test/publish/pause/rollback; immutable published versions; schema validation; tenant ownership enforced. | P0 | 5 | DFR1-013,DFR1-019 | automation,backend | To Do
DFR1-024 | DFR1-E08 | S4 (Days 10-12) | Implement workflow runtime and event trigger engine | Execute published workflows from domain/channel events with conditions, branches, timers and durable state. | Idempotent execution; bounded concurrency; timeout/retry/dead-letter; event replay safe; disabled workflow stops new runs. | P0 | 8 | DFR1-023,DFR1-013 | automation,runtime | To Do
DFR1-025 | DFR1-E08 | S4 (Days 10-12) | Implement approval, human task and escalation nodes | Support exact-payload approvals, approver authorization, expiry, reject, revalidation and audit. | Any changed action payload requires fresh approval; sensitive actions require configured approvals; human task can pause/resume workflow. | P0 | 5 | DFR1-023,DFR1-006 | automation,governance | To Do
DFR1-026 | DFR1-E08 | S4 (Days 10-12) | Build visual workflow editor and template catalogue | Provide node canvas, configuration panels, validation, simulation and templates for new lead, missed call, follow-up and site visit. | Saved graph reloads accurately; invalid flows cannot publish; test mode does not send real communications; keyboard/accessibility basics. | P0 | 8 | DFR1-023 | frontend,builder | To Do
DFR1-027 | DFR1-E05 | S4 (Days 10-12) | Implement voice provider adapter and inbound call lifecycle | Handle call webhooks, answer/bridge lifecycle, session correlation, caller lookup and human transfer using selected provider. | Real sandbox call works; inbound disabled unless org+agent+provider enabled; failures safely route to fallback/human; call state auditable. | P0 | 8 | DFR1-007,DFR1-011,DFR1-015 | voice,integration | To Do
DFR1-028 | DFR1-E05 | S4 (Days 10-12) | Implement voice conversation, transcription and post-call CRM update | Connect speech recognition/synthesis or realtime provider, language selection, structured extraction, summary and CRM task creation. | Call transcript/recording only under configured consent policy; extraction confidence; summary linked to call/contact/lead; human correction supported. | P0 | 8 | DFR1-027,DFR1-018 | voice,ai,crm | To Do
DFR1-029 | DFR1-E04 | S4 (Days 10-12) | Connect WhatsApp Business and validate inbound/outbound | Implement approved WhatsApp account/webhook, message send, template selection, media metadata and delivery status. | Real provider sandbox/test account verified; policy/template/window checks; opt-out respected; integration test evidence recorded. | P0 | 8 | DFR1-012,DFR1-014 | whatsapp,integration | To Do
DFR1-030 | DFR1-E04 | S4 (Days 10-12) | Connect Meta Messenger and Instagram messaging | Implement available approved Meta messaging capabilities, page/IG account connection, inbound webhook and outbound replies. | Only supported account/API scopes exposed; permission review and webhook verification; unsupported features clearly unavailable. | P1 | 8 | DFR1-012,DFR1-014 | meta,integration | To Do
DFR1-031 | DFR1-E04 | S4 (Days 10-12) | Connect email inbound/outbound and thread mapping | Implement selected email provider OAuth/API or SMTP/IMAP strategy, inbound parsing, outbound send and thread correlation. | Verified sender/domain and OAuth scopes; replies mapped to conversation; attachments scanned/limited; bounce/failure state recorded. | P0 | 5 | DFR1-012,DFR1-014 | email,integration | To Do
DFR1-032 | DFR1-E07 | S4 (Days 10-12) | Deliver assignment, follow-up and site-visit agents | Implement assignment, follow-up, site-visit scheduling and sales-operations agent templates. | Assignment respects capacity/territory/permissions; outbound actions gated; calendar availability not fabricated; human takeover supported. | P0 | 5 | DFR1-019,DFR1-022,DFR1-025 | agents,sales | To Do
DFR1-033 | DFR1-E10 | S5 (Days 13-15) | Deliver Dealsflo Copilot with authorized business queries | Natural-language questions, grounded CRM answers, summaries and proposed actions with source records. | Copilot only accesses authorized records; answers show source references; mutations are previewed and approved according to policy. | P1 | 5 | DFR1-015,DFR1-018 | copilot,genai | To Do
DFR1-034 | DFR1-E10 | S5 (Days 13-15) | Deliver generative property and communication content studio | Generate property descriptions, listing variants, WhatsApp/email/social drafts and multilingual content. | Drafts use approved facts only; user review before publishing/sending; language and tone configurable; generation usage metered. | P1 | 5 | DFR1-015,DFR1-017 | content,genai | To Do
DFR1-035 | DFR1-E10 | S5 (Days 13-15) | Deliver document and multimodal extraction MVP | Process PDFs, images and floor-plan images for text/metadata extraction, structured fields and reviewable summaries. | Upload is tenant-scoped and scanned/validated; source evidence and confidence shown; no claim of exact architectural measurement or legal advice. | P1 | 5 | DFR1-015,DFR1-016 | multimodal,documents | To Do
DFR1-036 | DFR1-E11 | S5 (Days 13-15) | Build organization AI and automation settings | Implement master AI switch, per-capability switches, per-agent/workflow activation, channel controls and policy configuration. | Defaults disabled; SIBVO entitlement + org enablement + connection + activation + permissions + consent/budget required; manual CRM remains usable. | P0 | 5 | DFR1-006,DFR1-017,DFR1-019,DFR1-023 | settings,governance | To Do
DFR1-037 | DFR1-E11 | S5 (Days 13-15) | Build no-code agent configuration studio | Allow authorized admins to configure agent instructions, language, tools, knowledge, triggers, approvals, limits and publish versions. | Schema-validated configs; tool grants constrained by admin permission; draft/test/publish/rollback; no agent self-granted permissions. | P1 | 5 | DFR1-019,DFR1-036 | agent-builder,frontend | To Do
DFR1-038 | DFR1-E11 | S5 (Days 13-15) | Build integration configuration and health UI | Show provider connection, scopes, webhook status, delivery failures, reconnect and disconnect. | No fake connected status; status reflects provider verification; secrets never rendered; authorized admins only. | P1 | 3 | DFR1-011,DFR1-012 | integration,frontend | To Do
DFR1-039 | DFR1-E09 | S5 (Days 13-15) | Deliver deal risk, pipeline and revenue baseline forecasts | Provide explainable stage-based risk and forecast baselines with model/rule metadata and feedback. | No unsupported probability claims; data sufficiency shown; factors, uncertainty, version, timestamp and actual outcomes stored. | P1 | 5 | DFR1-020,DFR1-022 | predictive,analytics | To Do
DFR1-040 | DFR1-E14 | S5 (Days 13-15) | Build AI and automation command center overview | Show enabled capabilities, agent status, workflow health, pending approvals, usage, channel health and key sales metrics. | All metrics derive from real persisted data; org-scoped; links to details; loading/empty/error states and permission checks. | P1 | 5 | DFR1-017,DFR1-019,DFR1-024,DFR1-036 | dashboard,frontend | To Do
DFR1-041 | DFR1-E15 | S5 (Days 13-15) | Run full end-to-end real-estate lead-to-visit scenario | Verify Instagram/WhatsApp/website enquiry to identity resolution, qualification, score, assignment, call, summary, match, message and visit. | Automated test or documented provider sandbox evidence; all records linked; disabled features do not run; failures recover without duplicates. | P0 | 8 | DFR1-009,DFR1-021,DFR1-022,DFR1-024,DFR1-028,DFR1-029 | e2e,release | To Do
DFR1-042 | DFR1-E15 | S5 (Days 13-15) | Run tenant isolation, authorization and abuse tests | Test cross-tenant access, prompt injection, unauthorized tools, replayed webhooks, budget exhaustion, consent/opt-out and approval bypass. | All critical tests pass; no tenant leakage; fail-closed on entitlement/policy uncertainty; findings recorded and blockers assigned. | P0 | 8 | DFR1-036,DFR1-041 | security,qa | To Do
DFR1-043 | DFR1-E15 | S5 (Days 13-15) | Prepare 15-day candidate and 30-day stabilization backlog | Review remaining gaps, provider approvals, performance, monitoring, deployment, backup/restore and customer onboarding. | Candidate status honestly classified; no placeholder presented as done; P0 release blockers and D16-D30 work have owners and acceptance criteria. | P0 | 3 | DFR1-041,DFR1-042 | release,planning | To Do
DFR1-044 | DFR1-E05 | Hardening (Days 16-30) | Deliver outbound voice campaigns with policy controls | Scheduled, segmented, consent-checked outbound campaigns, retries, suppression lists, callback and human transfer. | Real provider campaign tested; calling windows, consent/opt-out, concurrency, budgets, recording policy and failure handling enforced. | P0 | 8 | DFR1-027,DFR1-028,DFR1-036 | hardening,release | To Do
DFR1-045 | DFR1-E09 | Hardening (Days 16-30) | Add prediction feedback and model evaluation pipeline | Capture outcomes and evaluate lead scoring, deal risk and forecast error; introduce calibrated models only when data supports them. | Metrics, sample size, drift and limitations visible; model promotion requires evaluation and rollback. | P1 | 5 | DFR1-020,DFR1-039 | hardening,release | To Do
DFR1-046 | DFR1-E10 | Hardening (Days 16-30) | Add video understanding and richer floor-plan extraction | Add video summarization, timestamps/captions and improved floor-plan extraction/review. | Supported formats/limits explicit; extraction evidence visible; no unsupported claims about dimensions or condition. | P2 | 5 | DFR1-035 | hardening,release | To Do
DFR1-047 | DFR1-E11 | Hardening (Days 16-30) | Add custom business profile and pipeline builder | Support brokerage, developer/builder and hybrid profile with custom stages, fields, terminology and role-scoped dashboards. | Configuration versioned; data migration/backward compatibility tested; templates do not fork core CRM. | P1 | 8 | DFR1-008,DFR1-036 | hardening,release | To Do
DFR1-048 | DFR1-E11 | Hardening (Days 16-30) | Add custom scoring and recommendation policy builder | Allow admins to configure weights, hard constraints, exclusions and thresholds with preview/test and rollback. | Rules are explainable, versioned and tested against sample records; admin cannot bypass platform safety policy. | P1 | 5 | DFR1-020,DFR1-022,DFR1-047 | hardening,release | To Do
DFR1-049 | DFR1-E14 | Hardening (Days 16-30) | Add channel, agent, workflow and revenue analytics | Measure response time, conversion, call outcomes, agent success, workflow completion/failure and channel attribution. | Metrics definitions documented; calculations tenant-scoped and reconciled to source records. | P1 | 5 | DFR1-040,DFR1-041 | hardening,release | To Do
DFR1-050 | DFR1-E13 | Hardening (Days 16-30) | Complete retention, export, deletion and privacy controls | Implement configurable retention and deletion/export workflows for messages, calls, transcripts, documents and AI data. | Retention jobs auditable; legal holds/required records handled; secrets and sensitive content redacted from logs. | P0 | 5 | DFR1-028,DFR1-035,DFR1-036 | hardening,release | To Do
DFR1-051 | DFR1-E15 | Hardening (Days 16-30) | Performance, concurrency and resilience validation | Load-test webhook ingress, workflow execution, agent tasks, inbox queries and call concurrency; tune indexes and limits. | Targets set from expected pilot load; no duplicate execution; queue saturation and provider outage recovery demonstrated. | P0 | 8 | DFR1-024,DFR1-029,DFR1-041 | hardening,release | To Do
DFR1-052 | DFR1-E15 | Hardening (Days 16-30) | Production deployment, monitoring, backup and rollback | Deploy release candidate with migration plan, health checks, alerts, backups, restore drill and rollback runbook. | Restore verified; secrets managed; dashboards/alerts operational; release approval checklist signed. | P0 | 8 | DFR1-043,DFR1-051 | hardening,release | To Do
DFR1-053 | DFR1-E12 | Hardening (Days 16-30) | Complete SIBVO usage reconciliation and entitlement lifecycle tests | Verify usage summaries, subscription updates, seat changes, revocation, trial expiry, downgrade and webhook replay. | Idempotent events; bounded cache/revocation; reconciled usage; feature execution stops safely when entitlement removed. | P0 | 5 | DFR1-005,DFR1-017,DFR1-036 | hardening,release | To Do
DFR1-054 | DFR1-E04 | Hardening (Days 16-30) | Add channel provider resilience and reconciliation | Add webhook replay, provider health, rate-limit backoff, delivery reconciliation and operator diagnostics. | Failed/missed provider events recover safely; duplicate messages prevented; provider state visible. | P1 | 5 | DFR1-012,DFR1-014,DFR1-029,DFR1-030,DFR1-031 | hardening,release | To Do
DFR1-055 | DFR1-E07 | Hardening (Days 16-30) | Add agent evaluation, safety regression and marketplace catalogue | Evaluate task success, tool correctness, groundedness, latency, cost and policy violations; catalogue approved templates. | Versioned evaluation suite; unsafe regression blocks publish; marketplace templates are tenant-configurable, not trusted executable code. | P1 | 5 | DFR1-019,DFR1-021,DFR1-032 | hardening,release | To Do
DFR1-056 | DFR1-E08 | Hardening (Days 16-30) | Add workflow simulation, replay and advanced debugging | Provide dry-run simulation, event replay, node-level traces and safe retry/recovery. | Simulation cannot cause external side effects; replay idempotent; logs redact sensitive data. | P1 | 5 | DFR1-024,DFR1-026 | hardening,release | To Do
DFR1-057 | DFR1-E10 | Hardening (Days 16-30) | Add multilingual regional conversation and content quality suite | Test English, Tamil, Telugu, Hindi, Kannada and Malayalam for supported tasks, code-switching and fallback. | Quality measured by task and language; unsupported language/dialect is disclosed; human correction captured. | P1 | 5 | DFR1-028,DFR1-034 | hardening,release | To Do
DFR1-058 | DFR1-E15 | Hardening (Days 16-30) | Complete customer pilot, defect triage and release sign-off | Run controlled pilot with selected real estate businesses; triage defects, usability and provider issues. | No critical/high security defects; key journeys accepted; support/runbooks and known limitations published; release owner approves. | P0 | 8 | DFR1-049,DFR1-050,DFR1-052,DFR1-053 | hardening,release | To Do

## Epics
Epic Key | Epic Name | Outcome | Priority
DFR1-E01 | Repository Baseline, Architecture & Product Foundation | Verified baseline, documented architecture, stable modular boundaries and release environments | P0
DFR1-E02 | Real Estate CRM & Business Operating Core | End-to-end brokerage and builder/developer customer journeys using existing CRM foundations | P0
DFR1-E03 | Omnichannel Identity, Inbox & Conversation Timeline | One customer identity and one auditable timeline across supported channels | P0
DFR1-E04 | Communication Integration Gateway | Provider adapters, verified webhooks, outbound delivery, templates, retries and connection health | P0
DFR1-E05 | Voice AI & Call Operations | Real inbound/outbound AI calling, call state, transcript, summaries, handoff and CRM actions | P0
DFR1-E06 | AI Platform, Model Gateway & Knowledge | Provider-independent AI execution, retrieval, budgets, observability and evaluations | P0
DFR1-E07 | AI Workforce & Agent Builder | Specialized agents, configurable custom agents, typed tools, permissions and execution controls | P0
DFR1-E08 | Automation & Visual Workflow Builder | Event-driven visual workflows coordinating CRM, agents, predictions and channels | P0
DFR1-E09 | Predictive Intelligence & Next Best Action | Explainable lead/deal/inventory/revenue intelligence with feedback and evaluation | P0
DFR1-E10 | Generative, Document & Multimodal AI | Copilot, content generation, document/image/floor-plan/video understanding | P1
DFR1-E11 | Business, Agent, Workflow & Integration Studios | No-code customization for different real estate business models | P1
DFR1-E12 | SIBVO Identity, Entitlement, Seat & Billing Integration | SIBVO remains authority for identity, org, subscription, plans, entitlements and seats | P0
DFR1-E13 | AI Governance, Consent, Security & Usage Controls | Disabled-by-default AI, enablement hierarchy, approval policies, budgets, audit and privacy | P0
DFR1-E14 | Command Center, Analytics & Operational Intelligence | Unified management, adoption, funnel, agent, workflow, channel and revenue analytics | P1
DFR1-E15 | Quality, Reliability, Deployment & Release Readiness | End-to-end evidence, security, observability, recovery, runbooks and controlled release | P0

## Sprint Plan
Sprint | Days | Goal | Stories
S1 | 1–3 | Audit, architecture, SIBVO contracts, provider prerequisites and enablement policy | DFR1-001–007
S2 | 4–6 | CRM reuse, channel identity, conversations, webhook/outbox and communication gateway | DFR1-008–014
S3 | 7–9 | AI gateway, knowledge, usage, typed tools, core agents and predictive foundation | DFR1-015–022
S4 | 10–12 | Workflow runtime/editor, approvals, inbound voice, WhatsApp, Meta and email | DFR1-023–032
S5 | 13–15 | Copilot, content/document MVP, studios, command center and release candidate testing | DFR1-033–043
Hardening | 16–30 | Outbound voice campaigns, advanced prediction/multimodal, business studios, analytics, privacy, performance, deployment and pilot | DFR1-044–058

## Policies & Gates
Gate | Required condition | Failure behavior
SIBVO entitlement | Product plan enables requested feature | Deny new execution; show plan/entitlement reason
Organization setting | Organization explicitly enabled capability | Do not execute optional AI/automation
Provider connection | Required provider connected, verified and healthy | Queue safely or create human task; never claim sent/called
Resource activation | Agent/workflow configured, tested, published and active | Draft/paused resources cannot execute
User/resource authorization | Initiator and tool have permission for target record/action | Deny and audit
Consent/channel policy | Consent, opt-out, DND, template/window/calling-hour rules pass | Suppress action; preserve inbound event
Budget and limits | Usage budget, rate, concurrency, steps and time limits pass | Pause/deny according to configured policy
Approval | Required authorized human approved exact payload/version | Wait; no side effect
Disable action | Capability disabled during execution | Stop new work; safely cancel or finish in-flight work by policy
Manual CRM | AI disabled or unavailable | Manual CRM operations remain usable